## Slide 1: 4.03 Apply quality assurances to enhance product/service offerings.
Assess “product” readiness for sport/event (PM:146)

## Slide 2
To make sure all tasks have been completed and an event is ready for attendees, sports/event target markets might refer to their function sheets.
One aspect of identifying a segment of a sport/event target market involves identifying the heavy users.

## Slide 3: SIX WEEKS OR MORE PRIOR TO EVENT:
Determine size and scope of your event.
Determine your co-sponsors and invitees.
Check the arena master calendar for available dates.
Contact speakers and/or participants to determine availability.
Submit a Special Event Request online.
Confirm speakers and participants. Discuss time, date, and place, as well as dietary requirements, type of travel, payment, and technical needs.

## Slide 4
Determine event budget and secure funding sources.
Establish a publicity plan for the event.
Create print materials including invitations, brochures, posters, etc.
Announce/Advertise your event.
Book travel arrangements and communicate travel reimbursement guidelines to participants.
Request special services and equipment through Event Manager.
Select caterer and confirm date on their calendar.

## Slide 5: TWO WEEKS PRIOR TO EVENT:
Provide posters or flyers to Event Office for display.
Send reminder email to invitees.
Meet with all involved event staff to discuss logistics for the day of the event.
Complete all sections in Event Manger and ensure all supporting administrators have signed off the event as complete.
Finalize catering arrangements.
Check in with speakers and/or participants to confirm travel arrangements and event details.

## Slide 6: 3 - 5 DAYS PRIOR TO EVENT:
Confirm number of attendees with caterer.
Confirm any and all housekeeping requests.
Confirm media services needs.
Deliver proper “day of signage” (directional signs or sign for event door) to Events Office to have displayed

## Slide 7: DAY PRIOR TO EVENT
Send a final email reminder to invitees.
Purchase food, drinks, ice, tablecloths, and utensils not supplied by caterer.
Pick up parking passes for speakers.
Print/copy nametags and other materials as needed.
Hold a rehearsal to make sure everything is well-prepared and ready for participants and spectators.

## Slide 8: DAY OF EVENT:
Check room to make sure it is clean and holds the necessary equipment and furniture.
Meet caterer or set-up refreshments.
Place water at the podium for each speaker.
Set-up name tags and/or distribute programs.
If recording event, collect media services release forms from speakers and give to media services staff.

## Slide 9: ONE WEEK FOLLOWING EVENT:
Send speakers thank-you notes.
Pay vendors. Submit original receipts for payment/reimbursement.
Compile a list of all expenses incurred for the event.
Debrief with planning team. Discuss and document possible improvements in the process.
Document all event details, so that future groups may benefit from your experience